LINGUA Africa

Pre-Submission TODO & Verification Checklist

Lingo / Flagship — what must be done before the form is submitted

Deadline: 15 June 2026, 18:00 (form clock) / 23:59 WAT   ·   One stage, no resubmission, locks on submit.

How to read this: items are grouped by how blocking they are. The red band can sink the application or change its structure; the amber band materially weakens it if skipped; the green band is polish that raises the score. Boxes are tick-able. “SAMPLE” values already placed in the draft are realistic placeholders — every one must be replaced with a real figure or removed.

# 1. Blocking — resolve or the bid is at risk

These can disqualify, mislead a reviewer, or change the proposal's structure. Do these first. Two of these are also strategy-dependent (entity/recipient rule, category checkbox) and are still genuinely open — confirm them against the live RFP or by emailing hub-rfp@masakhane.io before committing.

|  | Item | Owner / source |
| --- | --- | --- |
| ☐ | Read the live RFP + FAQ Google Doc directly and confirm: exact category ceilings, the 12% overhead cap, whether the lead applicant must be the fund recipient, and the exact required sections/limits. Our figures come from the captured page; confirm at source. | Applicant |
| ☐ | Decide Q1(a) category selection. Primary = Category 3 (firm). Whether to also tick Category 1/2 for fallback eligibility depends on form mechanics — confirm whether extra boxes create funding eligibility or are scope-tags, by RFP text or a one-line email to hub-rfp@masakhane.io. | Applicant |
| ☐ | Confirm the lead/fiduciary entity and its legal status. Flagship SARL (Morocco) as lead. Resolve the org-type field so it matches public profiles (the Hugging Face org reads “non-profit”) — harmonise across form, letters, and web. | Applicant |
| ☐ | Publish model cards and a dataset card on the Hugging Face flagship-ai org before submitting. Reviewers of an openness grant will click the links; “No model card” directly contradicts the proposal's central claim. Highest-value, fully-in-your-control fix. | Tech lead |
| ☐ | Secure the letters of support (Q14, up to 3 PDFs): KIAMA deployment-commitment letter (channel into MINADER/MINEPIA & Health); Flagship–Sense Africa partnership/role letter; and, if at all possible, one ministry/programme content-owner or pilot-access letter. | Consortium leads |
| ☐ | Confirm the phase-one language list. Draft commits to 3 (Bulu, Fulfulde, Ghomala') — confirm these are the ones you can genuinely support first, or adjust. | PI + community lead |
| ☐ | Replace all [SAMPLE] metrics with real numbers or remove them: hours already collected, contributor count, target hours/speakers per language, pilot districts, extension-worker and producer counts. Plausible invented numbers you can't deliver are worse than honest ranges. | Data/QA + PI |
| ☐ | Verify every factual claim. Describe the 2024 launch accurately (public launch event, not “televised” unless you can evidence a broadcast). Reconcile Pinyin vs. Pidgin in the model list. Confirm the dataset name/size. Drop anything unverifiable. | Applicant |

# 2. Strongly recommended — materially strengthens the bid

Not disqualifying, but skipping these visibly weakens a competitive Category 3 application. Most of these are already drafted into the answers; this is about confirming the specifics behind them.

|  | Item | Owner / source |
| --- | --- | --- |
| ☐ | Name the pilot sites and user cohorts — specific districts/institutions, extension-worker count, producer count. “Pilot” without named sites reads as aspirational. | KIAMA + PI |
| ☐ | Finalise the compute request bottom-up (Q18b/c). Sum preprocessing/storage + ASR fine-tuning + TTS training + translation experiments + evaluation + pilot serving; request only what that justifies (up to $400K). Insert the total in Q18(b). | Tech lead |
| ☐ | Fill team names and FTE allocations (Q15), making gender balance and regional diversity visible — it is an explicit scoring criterion. | PI |
| ☐ | Insert existing model/dataset metrics (Q6/Q16) — languages, download/use counts, and any baseline scores you have. | Tech lead |
| ☐ | Confirm the ethics-review body / path (Q12), especially for the health extension. If no MoH content-owner and ethics path by submission, keep health to approved educational/public-health messaging only and remove any live patient-intake language. | Health pathway |
| ☐ | Fill the detailed budget tab to match the summary. The summary totals are set ($249,312 grand; $222,600 direct; $26,712 overhead). Confirm the unit costs and FTEs reflect your real local rates; the sheet recalculates and keeps the 12% cap automatically. | PI + admin |
| ☐ | Anchor the problem statement (Q2) in official data — add verified Cameroon rural-poverty / digital-divide figures with sources. Verify any statistic before quoting it. | PI |

# 3. Polish — raises the score, do if time allows

Low effort, real upside on a competitive call.

|  | Item | Owner / source |
| --- | --- | --- |
| ☐ | Add a privacy / governance / team page to lingo.cm so public due diligence finds consent and governance information, not a sparse site. | Tech lead |
| ☐ | Clarify open-release rules by artifact — which datasets/models/code/docs are open by default, what is restricted for safety/privacy, on what timeline, and how any future proprietary service stays separate from grant-funded public goods. | PI |
| ☐ | Optionally add Q5/Q6 (drafted) to reinforce the “spans multiple activities” story; include or omit as you prefer since you are Category 3. | PI |
| ☐ | Add partner bios / a one-page consortium sheet if the form or letters allow, to make the three-entity structure tangible. | Consortium |
| ☐ | Consider a university or community-org partner to deepen the community-engagement score, if one can be added quickly. | PI |

# 4. Open strategic questions (decide, don't just check off)

Q1(a) multi-category checkbox — genuinely unresolved. If extra boxes create real fallback funding eligibility with no framing downside, tick Category 3 (primary) + Category 1 (data) and not Category 2. If they are only scope-tags and the decision is single-category, tick Category 3 alone. Resolve via the RFP text or the hub-rfp email before submitting.

Income-replacement check — internal only, never in the application. Confirm the defensible PI salary line within the $222,600 direct budget over 18 months clears your personal threshold; if not, pair with existing support (Klaus Tschira/Alumnode) and ministry co-funding, or treat a sub-threshold award as a reason to stay employed.

Health go/no-go — keep health as a bounded extension unless you secure a MoH-backed content owner, a named pilot site, and an ethics path before submission. Evidence beats sector.

# 5. Submission mechanics

|  | Item | Owner / source |
| --- | --- | --- |
| ☐ | Paste each answer into the matching Submittable field and re-check it is within the field's word limit after any edits. | Applicant |
| ☐ | Upload the budget (.xlsx) at Q17(a); mirror the summary totals into the Q17(b) table. | Applicant |
| ☐ | Attach letters (≤3 PDFs) at Q14. | Applicant |
| ☐ | Complete contact, org email, web links, and the two history questions (applied before? / currently involved?). | Applicant |
| ☐ | Submit at least 24 hours early — 23:59 WAT on 15 June, no second stage, no edits after submit. | Applicant |

This checklist consolidates all advisor reviews. The red band is the difference between a strong idea and a reviewer-ready package; the amber band is the difference between reviewer-ready and competitive. Verify before you submit — the form locks.